## Sheet1
PROJECT CHARTER
GENERAL PROJECT INFORMATION
PROJECT NAME | Predictive Model for Student Placement and Calculation of Graduation Year
PROJECT SPONSOR | Tushar Topale
PROJECT MANAGER | Harshada Topale
EXPECTED START DATE | 2024-06-11
EXPECTED COMPLETION DATE | 2024-06-30
ESTIMATED COST | NA
GOALS, OBJECTIVES, DELIVERABLES
PROJECT OBJECTIVE | To develop a predictive model that forecasts students' year of graduation and their chances of securing job placements.
BUSINESS CASE | Addressing the lack of clear academic planning and career advice to improve timely graduation rates and enhance student employability.
GOALS/METRICS | • Achieve a prediction accuracy rate of at least 70% for both models. • Reduce the uncertainty in graduation timeframes and job placement prospects for students. • Timely submission of deliverables.
EXPECTED DELIVERABLES | • An application demonstration video in .mp4 format. • Source code in a zip file and a link to the GitHub repository. • Comprehensive project documentation including Project Charter, Software Requirement Specification, Work Breakdown Structure, Project Schedule, RAID Logs, Development Log, Traceability Matrix, Lessons Learned Log, and a final Project Report. • Two Excel files storing the final prediction results for year of graduation and job placement respectively.
PROJECT SCOPE AND SCHEDULE
WITHIN SCOPE | • Development of predictive models for student placement and graduation year. • Utilization of historical data and essential features for model training. • Storage of prediction results in separate Excel files for each model.
OUTSIDE OF SCOPE | • Real-time integration with university databases. • Post-graduation career tracking and analytics. • Extensive user interface design beyond demo requirements.
PROJECT RESOURCES AND COSTS
PROJECT TEAM | Chetna Bisht
SUPPORT RESOURCES | Google Colab for developing and testing the models.
COST ALLOCATION | Costs are limited to time investment, as all tools used for this project are available for free.
PROJECT BENEFITS AND CUSTOMERS
PROCESS OWNER | Harshada Topale
KEY STAKEHOLDERS | Harshada Topale
END CUSTOMER | Cloud Counselage Pvt Ltd.
PROJECT RISKS, CONSTRAINTS, ASSUMPTIONS
RISKS | • Data Quality and Availability: Inadequate or incomplete datasets may result in inaccurate predictions. • Overfitting/Underfitting: The models might not generalize well to new, unseen data if not properly validated. • Technology Dependence: Reliance on Google Colab could pose a risk if there are internet connectivity issues or changes in the free service policy.
ASSUMPTIONS | • Data Sufficiency: It is assumed that the datasets provided contain sufficient and relevant features needed to train effective predictive models. • Stable Requirements: The project requirements and scope will remain stable with no significant changes that could lead to project delays. • Tool Availability: Continued access to Google Colab or equivalent platforms throughout the project lifecycle without interruption. • Target Accuracy Achievable: The assumption that the models can achieve the targeted accuracy rate of at least 85% based on historical performance data and machine learning techniques.
CONSTRAINTS | • Technology Constraint: The project must be developed using Python within platforms like Google Colab. • Accuracy Requirement: The machine learning model must achieve a high accuracy rate, which might limit the choice of algorithms and require more sophisticated data preprocessing and model tuning strategies. • Output Format: Final predictions must be stored in separate Excel files, requiring specific formats and possibly the use of libraries like pandas for data manipulation and openpyxl or xlsxwriter for Excel output. • Resource Limitation: Being a solo project, time management becomes crucial, as all aspects of the project from development to documentation and testing need to be handled by a single individual. • Submission Deadline: The project must meet the submission deadlines for each deliverable, necessitating efficient project management and prioritization of tasks.