## Sheet1
PROJECT PLAN FOR EXECUTION PHASE
PROJECT NAME | Predictive models for graduation year calculation and placement status
PROJECT MANAGER | Harshada Topale
PROJECT DELIVERABLE | To develop a predictive model that forecasts students' year of graduation and their chances of securing job placements.
PROJECT SCOPE | Addressing the lack of clear academic planning and career advice to improve timely graduation rates and enhance student employability.
PROJECT START DATE | 2024-06-11
PROJECT END DATE | 2024-06-30
OVERALL PROGRESS | Completed
Sr No | Week/Duration | Activities | Task | Sub Task | Assigned to | Start Date | End Date | Hours required | Status
1 | Week 1 | INITIATION | Project Charter |  | Chetna Bisht | 2024-06-11 | 2024-06-11 | 2-3 | COMPLETED
1.1 |  |  | SRS Document |  | Chetna Bisht | 2024-06-11 | 2024-06-11 | 2 | COMPLETED
2 | Week 1-2 | PLANNING | WBS |  | Chetna Bisht | 2024-06-12 | 2024-06-12 | 1 | COMPLETED
2.1 |  |  | Project Schedule |  | Chetna Bisht | 2024-06-12 | 2024-06-12 | 3 | COMPLETED
2.2 |  |  | RAID Logs |  | Chetna Bisht | 2024-06-13 | 2024-06-18 | 2 | COMPLETED
3 | Week 2 | EXECUTION & MONITORING | Design | Design Specification | Chetna Bisht | 2024-06-14 | 2024-06-14 | 7-8 | COMPLETED
3.1 |  |  | Develop | Code | Chetna Bisht | 2024-06-15 | 2024-06-18 | 7-8 | COMPLETED
3.2 |  |  | Test | Test Plan | Chetna Bisht | 2024-06-17 | 2024-06-18 | 7 | COMPLETED
3.3 |  |  |  | Test Results | Chetna Bisht | 2024-06-18 | 2024-06-18 | 8 | COMPLETED
3.4 |  |  | Deploy | App Video | Chetna Bisht | 2024-06-20 | 2024-06-22 | 4 | COMPLETED
4 | Week 3 | CLOSURE | Lessons Learnt Project Report |  | Chetna Bisht | 2024-06-23 | 2024-06-27 | 6 | COMPLETED